**2019-20 Action Plan DRAFT**

**Including CDBG/HOME/ESG FUNDING APPROVAL**

**TIMELINE**

**ACTIVITY DEADLINE COMPLETED**

Release RFP’S (CDBG/HOME/ESG) 12/10/18 🞎

Town Hall meeting (Berston) Field House 12/18/18 🞎

ESG Mandatory Pre-Proposal meeting DOME 1/9/19 🞎

Agency Application workshop– Dome Auditorium 1/9/19 🞎

Public Needs Hearing – Berston Field House 4:30pm 1/10/19 🞎

CDBG/HOME/ESG RFP Submission Deadline 1/31/19 🞎

CWAC Committee review applications and 2/20, 2/27, & 3/6/19 🞎

make recommendations

DCED publishes notice of availability of draft 4/12/19 🞎

2019-20 Action Plan and beginning of comment period

City Council Public Hearing

*(Proposed 2019-20 Action Plan)* 4/22/19 🞎

Thirty-day comment period on Action Plan ends 5/13/19 🞎

(31 days)

City Council Meeting

*(Requesting approval of 2019-20 Action Plan)* 5/13/19 🞎

DCED Submits Action Plan 5/15/19 🞎

HUD 45-day review period 5/15/19 – 7/01/19 🞎

Funds available for use (estimated) 7/01/19 🞎